## Project Planner
Master_Plan
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 3 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | AUG |  | SEPTEMBER |  |  |  | OCTOBER |  |  |  |  | NOVEMBER |  |  |  | DECEMBER |  |  |  | JANUARY |  |  |  |  | FEBRUARY |  |  |  | MARCH |  |  |  | APRIL |  |  |  | MAY
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38
Week | [5 empty] | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
BI3051 | 3 | 10 | 3 |  | 25%
Sample Analysis | 1 | 6 | 1 |  | 100%
Data organising | 1 | 6 | 1 |  | 35%
Statistical analysis | 7 | 9 |  |  | 10%
R Workshop | 7 | 1 |  |  | 85%
Literature Excel sheet | 3 | 4 |  |  | 85%
Outline | 2 | 5 |  |  | 50%
Introduction (10p) | 5 | 2 |  |  | 60%
Hypothesis | 5 | 2 |  |  | 75%
Aim (1/2 p) | 6 | 5 |  |  | 100%
Method (13p) | 2 | 5 |  |  | 60%
Results | 16 | 10 |  |  | 0%
Discussion (11p) | 26 | 8 |  |  | 50%
Christmas break | 17 | 2 |  |  | 0%
Easter break | 35 | 1 |  |  | 1%
Activity 16 | 10 | 5 |  |  | 80%
Activity 17 | 11 | 2 |  |  | 0%
Activity 18 | 12 | 6 |  |  | 0%
Activity 19 | 12 | 1 |  |  | 0%
Activity 20 | 14 | 5 |  |  | 0%
Activity 21 | 14 | 8 |  |  | 44%
Activity 22 | 14 | 7 |  |  | 0%
Acknowledgement | 35 | 1 |  |  | 12%
Abstract (1p) | 35 | 1 |  |  | 5%
Finishing | 36 | 3 |  |  | 0%
Deliver | 38 | 1 |  |  | 50%